## Sprint Backlog
SPRINT 1 (10/25/2019 - 11/3/2019)
Name | Description | Time to Complete
Brainstorm Ideas | Come up with ideas for the project | 2 days
Install Unity and GitHub | Install the correct version of Unity and install GitHub desktop to manage version control | 1 hour
Watch tutorials about Unity | Learn how Unity is used so we know the basic functionality | 2 days
First draft of background art | Create first draft of custom background art for each scene | 7 days
First draft of card art | Create first draft of custom deck designs for each card | 7 days
Create main menu screen | Implement a very basic main menu with buttons to instructions scene and a button to the game play scene | 3 hours
Create instruction menu screen | Implement a very basic main menu with first draft of instructions and a button to go back to the start menu | 3 hours
Create game screen | Implement a very basic game screen where the main game will take place | 3 hours
Implement card assets | Upload first draft of deck into Unity to begin development | 1 hour
Randomly shuffle deck | Write software to randomly shuffle the deck between the user and AI | 1 hour
Assign cards to human and AI | Write software that stores what cards each player has and can update what cards each player looses or gains | 1 hour
Place cards in pile | Write software that places the card sprites into the center of the page and allows the user to see the last 5 cards played | 3 hours
Place cards on opposite ends of screen | Write software that can send the card sprites to the opposite ends of the screen so the user can see where the cards are coming from | 3 hours
Implement slap button placeholder | Create a button that the user will click of they can receive cards | 1 hour

## Product Backlog
SPRINT 1 (10/25/2019 - 11/3/2019)
Name | Description | Time to Complete
Brainstorm Ideas | Come up with ideas for the project | 2 days
Install Unity and GitHub | Install the correct version of Unity and install GitHub desktop to manage version control | 1 hour
Watch tutorials about Unity | Learn how Unity is used so we know the basic functionality | 2 days
First draft of background art | Create first draft of custom background art for each scene | 7 days
First draft of card art | Create first draft of custom deck designs for each card | 7 days
Create main menu screen | Implement a very basic main menu with buttons to instructions scene and a button to the game play scene | 3 hours
Create instruction menu screen | Implement a very basic main menu with first draft of instructions and a button to go back to the start menu | 3 hours
Create game screen | Implement a very basic game screen where the main game will take place | 3 hours
Implement card assets | Upload first draft of deck into Unity to begin development | 1 hour
Randomly shuffle deck | Write software to randomly shuffle the deck between the user and AI | 1 hour
Assign cards to human and AI | Write software that stores what cards each player has and can update what cards each player looses or gains | 1 hour
Place cards in pile | Write software that places the card sprites into the center of the page and allows the user to see the last 5 cards played | 3 hours
Place cards on opposite ends of screen | Write software that can send the card sprites to the opposite ends of the screen so the user can see where the cards are coming from | 3 hours
Implement slap button placeholder | Create a button that the user will click of they can receive cards | 1 hour
SPRINT 2 (11/4/2019 - 12/1/2019)
Name | Description | Time to Complete
Final draft of background | Implement final draft of background art in project | 28 days
Final draft of cards | Implement final draft of cards art in project | 28 days
Music | Create and implement custom music to play | 28 days
Sound effects | Create and implement custom sound effects for certain gameplay scenarios | 28 days
Winner page | Display a screen with text saying the user won and ask to play again | 2 hours
Looser page | Display a screen with text saying the user lost and ask to play again | 2 hours
Implement face card cases | Write software to deal with the face card corner cases. Ace: 4 tries to get a face card, King: 3 tries, Queen: 2 tries, Jack: 1 try | 12 hours
Final draft of instructions | Revise instructions for clearer understanding. Implement multiple scenes to show examples of gameplay | 10 hours
Card counter | Write software to keep track of how many cards each player has | 1 hour
AI difficulties | Create easy, medium, and hard AI modes. These modes will only differ in how fast the AI will slap the button | 3 hours
Choose AI page | Create a page to select AI difficulty, either easy, medium, or hard. | 2 hours
Slap button | Write software that when the button is clicked, whichever player clicks the button first wins the cards | 4 hours
Card animations | Write software to show cards moving across the screen | 28 days
Update all sprites | Update all sprites and artwork to the final drafts | 5 days
Test project | Once project is finsihed, test code for bugs and fix them | 7 days
Documentation | Complete all required documentation | 28 days